- Purpose

This document sets out a project scope and work plan to further develop and enhance the digital and data systems for the Emergency Response Rooms, the Localization Coordination Council, the Localization Hub, and partners. It contextualizes the implementation plan from October 2025 to March 2026 to be achieved as part of the capacity-building component of the FCDO-funded Supporting Mutual Aid Grassroots Initiatives in Sudan program, led by Proximity2Humanity.

- Background

Since the start of the war in 2023, mutual aid groups, like the Emergency Response Rooms, have led localized humanitarian efforts, largely due to their local knowledge, decentralized structures, and ability to continue operating while larger, international groups encounter access constraints. Supporting local organizations, especially informal networks like the ERRs, can be wildly inefficient and difficult to navigate for international donors. Recognizing this inefficiency and the negative impacts it had on resourcing lifesaving activities across Sudan, the ERRs formed the Localization Coordination Council to better share information and resources, while helping donors and INGOs reach these groups across the country.

To further enhance the operations and administration of resources that were intended for ERRs, the LCC supported the establishment of a standardized learning and accountability tool (F-system) that was able to streamline reporting and funding flows. In addition, they established an operations unit, known as the Localization Hub, to oversee this work and build the capacity of ERRs as the movement grew. The Localization Hub was incubated by Gisa Group, providing the necessary funding to purchase equipment, build tools, and staff key positions to keep funding flowing in an accountable and systematic manner.

After over two years of conflict, the ERRs have gained international attention, and with it an increase in financial support provided directly to these groups. The Localization Hub now administers a resource pool that is 5x larger than when it started, with increased responsibilities to inform, track, and report on the utilization of resources. They play a critical role in providing data that informs locally-led resource planning and training for ERR volunteers on these systems. To keep pace, they need enhanced tools, systems, and processes to maintain the principles of mutual aid, keep support costs low, and enhance information sharing and reporting in ways that do not burden grassroots volunteers.

Gisa Group continues to provide accompaniment and capacity building support to the Localization Hub, as well as directly to base ERRs in order to support the LCC and the larger ERR network to manage more complex grants and increased funding while retaining their decentralized, transparent, and solidarity-based movement.

- Goals and Objectives

Goal: Support the Localization Hub, the LCC and partners in co-designing and developing the digital infrastructure that will improve the capacity of mutual aid groups to manage up to 5% of the total humanitarian funding for Sudan, through transparent, locally owned, and volunteer-driven coordination.  In deploying this digital infrastructure our objectives are:

- Open-Source and Locally Owned Platform: Develop an open-source digital infrastructure that builds on existing systems, drives local decision-making, and allows community members to adapt, extend, and maintain to meet evolving needs.

- Community Learning: Extend digital platforms beyond reporting to foster storytelling, peer exchange, and collaboration across mutual aid groups and partners.

- System Integration: Link the Localization Hub and LCC tools with broader humanitarian systems to ensure interoperability, data sharing, and coordination.

- What we have built so far

Gisa has played a key role in strengthening the Localization Hub, helping to establish its core systems and structure. We have also provided research and communications support, including the report We Are the System Now, which documents the rise of the ERRs, explains how they are organized and funded, and offers practical recommendations to build stronger, more equitable partnerships with international actors. In parallel, we are improving connectivity for ERRs and other local groups by providing Starlinks, along with training and advocacy to ensure that critical information continues to flow from the ground.

On the digital side, we have built around the F-System to develop 3 key components to the ERR Digital Infrastructure.

- Mutual Aid Portal - The Mutual Aid Portal connects the LCC, ERRs, and partners through a shared digital platform for planning and resource allocation built around the F-System. It replaces fragmented processes currently managed through multiple Google Sheets, Drives, and local files. The portal aims to improve coordination, reduce administrative workload, and build a shared knowledge and learning hub that strengthens collaboration among volunteers and partners.

- ERR App is built for frontline volunteers and designed around the F-System to help them coordinate projects with State ERRs and the LCC. It allows users to securely submit information, manage activities, and communicate throughout each project cycle, even when working offline in low-connectivity areas.

- ERR Database The ERR Database is a secure PostgreSQL system that underpins both the Mutual Aid Portal and the ERR App. It structures all F-System data, including grants, projects, and reports, into a single, reliable source of information that supports coordination, transparency, and informed decision-making.

Live Features The core F-System functions are already operational across the Mutual Aid Portal and ERR App. These include partner  forecasting and back-donor grant management, activity grant distribution and allocation, digital submission and feedback on F1 forms, automated MOU generation, structured F4/F5 reporting, and project tracking across F-Systems. The systems also support secure user and room registration and OCR/AI-assisted data entry.

Related Systems: In addition to the core digital infrastructure, we are developing several related components that extend the functionality of the F-System and connect it with wider humanitarian and financial systems.

- Looker Studio Dashboards: Interactive dashboards built around F-System data from Google Sheets are being integrated into the Mutual Aid Portal to visualize forecasts, funding flows, and project progress in real time.

- P2H Database: A full scale PostgreSQL database is being developed which will enable  e2e reporting for both donor and ground actors to track grant data, replacing the existing Google Sheets. The integration between the ERR and P2H databases will demonstrate interoperability between local and INGO systems, and serve as a template for other initiatives.

- ERR Bot: Messenger-based bots are being developed to automate F-System documentation processes, such as data collection, reporting, and notifications, directly within commonly used communication platforms.

- Geospatial Mapping: In collaboration with MapAction, geospatial mapping tools are being developed to visualize project locations, needs, and funding coverage, which will be integrated into the Mutual Aid Portal.

- Stablecoin Payments (CHATS): Supported by Mercy Corps and Stellar Foundation we will integrate with the CHATS payments system to enable real-time tracking of stablecoin-based payments. Data from CHATS will be incorporated into the Mutual Aid Portal in Q1 2026 to enhance financial transparency and traceability.

- Digital Support Roadmap

From October 2025 to March 2026, the digital support roadmap focuses on strengthening digital infrastructure and improving experience for the Localization Hub, frontline volunteers, and partners. A full product roadmap is also covered in FAQ5.  The Mutual Aid Portal, ERR App, and other related tech for mutual aid groups in Sudan we  breakdown our product and roadmap into Priority (P0) features and Enhancements (P1-P2). We are also separately scoping solutions to support the Localization Hub with internal operations.

LCC Systems Priority Features (P0): The next phase of development focuses on dashboards and data tools that improve visibility and coordination. Key features include decision-support dashboards for the LCC, fund allocation tracking, ERR mapping, and data export functions. Database priorities include integrating historical data, linking with the P2H database, and introducing row-level security (RLS) for data protection.

LCC Systems Enhancements (P1–P2): Planned upgrades include an F6 community feedback component, offline uploads in the ERR App, MOU e-signatures, payment tracking modules, and new features for F2 approvals and community validation. Additional priorities involve integrating the needs assessment calculator, enabling photo-based reporting via the ERR Bot, and expanding interoperability by connecting the ERR Database with SHF and CCS systems.

Systems Onboarding and Training Onboarding the Localization Hub, LCC, National NGOS, ERRs and donors to ERR Systems. Detailed onboarding and training plans covered  in FAQ1.

Community Development Training and scaling a community of local developers and allies to achieve long-term open-source system sustainability. Approach to community development covered in FAQ2.

Localization Hub Organizational Support and Systems Provide organizational support for the Localization Hub in the support of mentorship and training alongside technological solutions. Deploy effective internal finance and HR systems for the Localization Hub to support their development and processes.

- Deliverables

By March 2026, we are targeting the following deliverables:

| Month | Deliverables for Digital Product | Deliverables for System Onboarding and Community Development |
| --- | --- | --- |
| October | 1. ERR App integration with MAP to facilitate two-way communication . | 1. Completed User-Acceptance Testing (UATs) with Localization Hub on Mutual Aid Portal 2. Weekly development and training sessions with Localization Hub teams. 3. Evaluation indicator plan, with baseline figures, to measure outcomes in Section 5 |
| November | 1. Fully operational Mutual Aid Portal, ERR App, and database 2. P2H database and integration with ERR systems 3. Looker Studio dashboards and integration into MAP 4. ERR App offline capability, reporting while offline | 1. In-person workshop in Kampala with the Localization Hub, LCC working groups, and State ERRs. 2. Full migration of Localization Hub team and F-System tracking processes to the Mutual Aid Portal. 3. Integration of MAP training in F-System Scaling sessions with ERRs 4. Weekly development and training sessions with LCC and Localization Hub teams |
| Milestone 1 Delivered |  |  |
| December | 1. ERR messenger-based bots and integration with the database 2. Expansion of Partner Portal functionality beyond forecasting to include needs assessment data conducted by partners. 3. Optimization and continuous improvements to systems 4. Localization Hub finance and HR system selection | 1. Completed onboarding of 3 out of 13 States to Mutual Aid Portal to be measured by training sessions, registration, and at least a number of F1’s uploaded into the system from each state to be defined by evaluation indicator plan. 2. Integration of MAP training in F-System Scaling sessions with ERRs 3. Weekly development and training sessions with LCC and Localization Hub teams 4. Public launch of the External ERR developer community 5. Onboarding partners to provide needs and resources data beyond cash distribution and/or integrating with data sources that capture this information. |
| January | Optimization and continuous improvements to systems | 1. In-person workshop in Kampala with the Localization Hub, LCC working groups, and ERRs. 2. Completed onboarding of 6 out of 13 States to Mutual Aid Portal to be measured by training sessions, registration, and at least a number of F1’s uploaded into the system from each state to be defined by evaluation indicator plan. uploaded into the system from each state. 3. Weekly development and training sessions with LCC and Localization Hub teams 4. Onboarding Localization Hub to new finance and HR systems. |
| Milestone 2 Delivered |  |  |
| February | 1. Optimization and continuous improvements to systems 2. F6 Component to Mutual Aid Portal | 1. Completed onboarding of 9 out of 13 States to Mutual Aid Portal to be measured by training sessions, registration, and at least a number of F1’s uploaded into the system from each state to be defined by evaluation indicator plan. 2. Weekly development and training sessions with LCC and Localization Hub teams |
| March | Optimization and continuous improvements to systems | 1. Completed onboarding of 13 out of 13 States to Mutual Aid Portal to be measured by training sessions, registration, and at least a number of F1’s uploaded into the system from each state to be defined by evaluation indicator plan. 2. Weekly development and training sessions with LCC and Localization Hub teams |
| Milestone 3 Delivered |  |  |

- Outcomes

Based on the deliverables in section 6, Gisa expects the following key outcomes:

- Efficient Localization Hub internal systems for grant management, HR, finance, and communications.

- More time for the Localization Hub to spend on analysis and storytelling, instead of organizing files and data.

- Clear, easy-to-understand data and tools supporting local planning and resource allocation.

- Improved user experience for frontline volunteers submitting work plans and reporting on their achievements, and requesting support.

- Stronger communications and visibility for frontline volunteers participating in F-System.

- Enhanced tracking of grants, funding flows, priorities, and needs across ERRs.

- Reduced disbursement/transfer lag time between LoHub and Base ERR.

- Improved local development capability to enhance and  maintain the system.

- Improved coordination with international and national NGOs and agencies through connected systems.

- Mapping of needs, resources, and support to ERRs.

- Increased digital literacy and system ownership among ERR and LoHub teams through ongoing onboarding and training.

- Monitoring and Evaluation

Project deliverables, outcomes, and updates will be tracked during weekly implementation sessions together with P2H, Localization Hub, and stakeholders. We will use this spreadsheet to track progress: ERR F-System User Stories and Applications. Alongside the Weekly Dev sessions, we will have 2 weekly mechanisms to deliver on the plan. The project team will also submit 3x lightweight reports at the end of November, January, and March to be distributed across stakeholders.

- Budget and Schedule

The budget required to support this project is $130,000 which includes $108,500 for digital deliverables & software costs, travel ($10,000) and overhead ($11,500). Payments to be made following milestones tied to deliverables in Section 4.

- 40% on signing to help deliver Milestone 1

- 30% after Milestone 1 delivered

- 15% after Milestone 2 delivered

- 15% after Milestone 3 delivered

- FAQs

FAQ1: What is the plan for onboarding stakeholders to the new systems?

From October 2025 to March 2026, onboarding and training efforts will focus on gradually integrating core stakeholders into the Mutual Aid Portal (MAP) and ERR App, beginning with the Localization Hub and expanding to ERRs, LCC partners, and donors. LCC and ERR onboarding will look to overlap with the F-System Scaling and Capacity Building sessions scheduled from October to December.

Localization Hub (Oct-Nov): The first phase will onboard the Localization Hub to the Mutual Aid Portal. This includes migrating from Google Sheets and Drives to MAP to simplify grant and project tracking. By automating data uploads and connecting information in the backend, this phase aims to reduce manual coordination and strengthen data consistency across the system. This phase will also transition current analytics platforms into the MAP and set up access for key partners (eg. P2H) to maintain real-time reporting capabilities.

Emergency Response Rooms (Nov-Dec): The ERR App will enable two-way communication between field volunteers and central planning teams. Onboarding will continue with State ERRs from November to December 2025, followed by Base ERRs from December 2025 to January 2026. Since September, we have already registered 69% of State ERR users and 9 LCC working groups in the new system. From Nov-Dec our goal will be to increase the adoption of using the app to submit F-System files.

LCC Partners and Donors (Dec-Jan): LCC partners will be onboarded to the Mutual Aid Portal between December 2025 and January 2026 to improve visibility and coordination on grants, projects, and reporting. Donor and intermediary partner engagement, which began in October 2025 and continues through February 2026, focuses on expanding participation, increasing the number of partners submitting forecasts, and enabling partners to upload grants directly into the Portal for LCC review and distribution.

FAQ2: What is the plan for long term sustainability and maintenance of systems?

From October 2025 to March 2026, we will be expanding our community of open-source developers to support long-term sustainability of systems. Community development will focus on two areas.

- Weekly Dev Sessions with the Localization Hub and LCC developers will take place throughout the period, covering software development, database management, and system maintenance to strengthen local technical capacity and ownership of the digital infrastructure.

- External ERR: Since January 2024, we have started to develop a community of developers, designers and engineers dedicated to supporting the development of digital systems for the Emergency Response Rooms. From December 2025 we aim to publicize and scale this initiative to help contribute to the open-source ecosystem.

- Pursuit of private sector partnerships that can contribute funds and expertise to improve the systems.

FAQ3: What is the plan to support the Localization Hub and ERRs outside of digital systems to ensure long-term sustainability?

Organizational Support:

- Organizational Strengthening: Support development of the Localization Hub into a strong and independent organization capable of sustainably and adaptably  supporting a wide range of ERR activities.

- Operational Capacity: Improve the practical capacity of the Localization Hub to process and manage growing volume of grants and partnerships by improving internal systems, expanding key staffing, and ensuring effective governance and sustainability measures.

- Institutional Learning: Capture lessons learned by the ERR system to ensure that these can be fully utilized to advance innovation both internally and in the wider humanitarian system.

- Communication Support: Support the Localization Hub to deploy Starlinks and provide basic training to five key ERRs, enhancing their ability to communicate, document activities, and  advocate for themselves Help the Lohub in developing  compelling stories about the FCDO grant to strengthen recognition and long-term funding opportunities.

Research:

- Policy Briefings: Produce concise, policy-oriented papers highlighting key insights and innovations from the ERR ecosystem to inform humanitarian policy and practice.

- Evidence and Advocacy: Conduct advocacy, including through two events, using research to build confidence in localized humanitarian models, attract further funding, and amplify the ERR approach globally as well as credibility of ERRs as humanitarian actors.

- Protection Research: Explore ways to document threats and violence against mutual aid groups, including early warning and protection mechanisms.  Collect raw data on these incidents and conduct analysis to formulate actionable recommendations for the protection of vulnerable volunteers.

FAQ4: How are you thinking about system interoperability?

Building the system interoperable and open-source, our aim is to be able to capture information that can be used by ERRs and partners for effective resource planning and allocation. Below is a table representing our existing and planned integrations.

FAQ5: What is your system architecture?

FAQ6 What is the full product roadmap and priorities?

Below is a list of product features for each application. TBC means additional scoping required to determine level of effort.

| Count | Priority | Theme | Feature | ERR App | ERR Bot | Mutual Aid Portal |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | ✅ Live | Donor Inputs | Donor Forecast Dashboard | N/A | N/A | ✅ |
| 2 | ✅ Live | Donor Inputs | Donor raise grant calls in system | N/A | N/A | ✅ |
| 3 | ✅ Live | F0 Needs Assesment and Grant Allocation | LCC Partner raising funding cycle (one-off, emergency, tranches) | N/A | N/A | ✅ |
| 4 | ✅ Live | F0 Needs Assesment and Grant Allocation | Allocation of funds across tranches and states | N/A | N/A | ✅ |
| 5 | ✅ Live | F0 Needs Assesment and Grant Allocation | Visibility of funds allocated, committed, pending, remaining | N/A | N/A | ✅ |
| 6 | ✅ Live | F1 Upload and Submission | Base and State ERR visibility of funds available to begin sending F1s | ✅ | Dec-25 | ✅ |
| 7 | ✅ Live | F1 Upload and Submission | F1 Work Plan form submission using ERR App or MAP incl. OCR/AI processing | ✅ | Dec-25 | ✅ |
| 8 | ✅ Live | F1 Upload and Submission | F1 form visible to State and editable with feedback | ✅ | N/A | ✅ |
| 9 | ✅ Live | F1 Upload and Submission | Feedback thread and edit history | ✅ | N/A | ✅ |
| 10 | ✅ Live | F1 Upload and Submission | Pre-assign F1s to grants before F2 approvals | N/A | N/A | ✅ |
| 11 | ✅ Live | F2 Selection and Approvals | Upload F2 approvals to F1 projects | TBC | TBC | ✅ |
| 12 | ✅ Live | F2 Selection and Approvals | Assign or resassign F1s to states, grant calls, and cycles | N/A | N/A | ✅ |
| 13 | ✅ Live | F3 MOU | Auto-generate MOU from approved F1/F2 | N/A | N/A | ✅ |
| 14 | ✅ Live | F4 & F5 Project Implementation & Reporting | Final F4/F5 submission | ✅ | Dec-25 | ✅ |
| 15 | ✅ Live | F4 & F5 Project Implementation & Reporting | Structured F4/F5 form storage | ✅ | Dec-25 | ✅ |
| 16 | ✅ Live | F4 & F5 Project Implementation & Reporting | Project tracker and viewer | TBC | TBC | ✅ |
| 17 | ✅ Live | UI/UX | Disguise app as calculator | ✅ | N/A | N/A |
| 18 | ✅ Live | UI/UX | ERR Registration | ✅ | TBC | ✅ |
| 19 | ✅ Live | UI/UX | User Registration | ✅ | TBC | ✅ |
| 20 | 🔴 P0 | Dashboards | Dashboard: F-System | N/A | N/A | Nov-25 |
| 21 | 🔴 P0 | Dashboards | Dashboard: P2H Grants | N/A | N/A | Nov-25 |
| 22 | 🔴 P0 | Dashboards | Dashboard for weekly LCC decision support | N/A | N/A | Nov-25 |
| 23 | 🔴 P0 | Dashboards | Dashboard: Final reports and summary view | N/A | N/A | Nov-25 |
| 24 | 🔴 P0 | Dashboards | Export data from dashboards that can be shared | N/A | N/A | Nov-25 |
| 25 | 🔴 P0 | Dashboards | ERR Mapping | TBC | N/A | Dec-25 |
| 26 | 🔴 P0 | Database | RLS for database tables | Nov-25 | Dec-25 | Nov-25 |
| 27 | 🔴 P0 | Database | Integration with Proximity database | N/A | N/A | Nov-25 |
| 28 | 🔴 P0 | F0 Needs Assesment and Grant Allocation | Upload copy of calculator tool output to allocation decision for tracking | N/A | N/A | Dec-25 |
| 29 | 🔴 P0 | F0 Needs Assesment and Grant Allocation | Needs assessment integration | TBC | TBC | TBC |
| 30 | ✅ Live | UI/UX | Upload new logo | ✅ | Dec-25 | ✅ |
| 31 | 🔴 P0 | UI/UX | Roles Based Access | Oct-25 | Dec-25 | Oct-25 |
| 32 | 🟠 P0 | UI/UX | Offline uploads using ERR App | Nov-25 | Dec-25 | N/A |
| 33 | 🟠 P1 | F0 Needs Assesment and Grant Allocation | More detailed ERR registration | Jan-26 | N/A | Jan-26 |
| 34 | 🟠 P1 | F0 Needs Assesment and Grant Allocation | Integrate Calculator tool into MAP | N/A | N/A | Feb-26 |
| 35 | 🟠 P1 | F2 Selection and Approvals | Gather F2 signatures from community members | Feb-26 | N/A | Feb-26 |
| 36 | 🟠 P1 | F2 Selection and Approvals | Notify ERRs of F2 selection outcome | Dec-25 | Dec-25 | Dec-25 |
| 37 | 🟠 P1 | F3 MOU | MOU E Signature | TBC | TBC | TBC |
| 38 | 🟠 P1 | F4 & F5 Project Implementation & Reporting | Upload F4/F5 photo or fill in form via bot | N/A | Dec-25 | N/A |
| 39 | 🟠 P1 | F4 & F5 Project Implementation & Reporting | Payment tracking module + dashboard | TBC | TBC | TBC |
| 40 | 🟠 P1 | F4 & F5 Project Implementation & Reporting | Project completion: end status + timestamp | TBC | TBC | TBC |
| 41 | 🔴 P0 | Database | Migrate historical data into Mutual Aid Portal | N/A | N/A | Dec-25 |
| 41 | 🟠 P1 | F6 Reporting to Community & Donors | F6 Component in MAP and ERR App | Feb-26 | Feb-26 | Feb-26 |
| 41 | 🟡 P2 | Database | Integration with SHF & CCS | TBC | TBC | TBC |